## Summary
Executive Summary
Rating | Count
Critical | 1
High | 2
Medium | 1
Low | 0
Total risks | 4
Open items | 4
MFA control failure rate | 30%

## Risk Register
IT Services Co. (Fictional) - Splunk Risk Register
Data source: simulated authentication logs (it_services_co_auth_logs.csv), 180 events, Oct 2026. All names, IPs and events are fictional.
ID | Risk | Description / Splunk result | Likelihood (1-5) | Impact (1-5) | Risk Score | Rating | Recommended Mitigation | Risk Owner | Target Date | Evidence File | Framework Mapping (suggested) | Status
R-01 | Terminated employees retain active access | 3 successful logins by 2 terminated users (bthomas x2, cdavis x1) from external IPs, including CLIENT_DB, FILE_SERVER and VPN. Offboarding failed to disable accounts. | 5 | 4 | 20 | Critical | Disable both accounts immediately; review access granted during the logins; add an automated HR-to-IT offboarding check and a monthly terminated-user access review. | IT Operations / IAM Lead | Immediate (24 hrs) | finding01_terminated_user_access.png | NIST CSF 2.0: PR.AA ¦ ISO/IEC 27001:2022: A.5.18 | Open
R-02 | Brute-force attempt on admin account | 26 failed logins against admin account asharma in about 3 minutes (around 03:12) from external IP 185.220.101.9, all against ADMIN_PORTAL. 34 failed logins in total in the dataset. | 4 | 4 | 16 | High | Block the source IP; enable account lockout and rate limiting; restrict admin portal to VPN; create a Splunk alert for 5+ failures in 5 minutes. | Security Operations Lead | 7 days | finding02_failed_login_burst.png; finding02_source_ip.png | NIST CSF 2.0: DE.CM ¦ ISO/IEC 27001:2022: A.8.5, A.8.16 | Open
R-03 | Accounts logging in without MFA | 3 of 10 active accounts logged in without MFA: rpatel (Admin), tnguyen (Developer), pjones (Analyst). 45 successful no-MFA logins by active users. | 4 | 4 | 16 | High | Enforce MFA enrollment, starting with the admin account; block password-only logins by policy. | IAM Lead | Admin: 7 days; others: 30 days | finding03_no_mfa_accounts.png | NIST CSF 2.0: PR.AA ¦ ISO/IEC 27001:2022: A.8.5 | Open
R-04 | Logins outside normal hours | 6 successful logins between 20:00 and 06:00: rpatel x2, bthomas x2, cdavis x1, tnguyen x1. Three of the six are by terminated users (overlaps with R-01). | 3 | 3 | 9 | Medium | Alert on successful after-hours logins to admin and client systems; require manager approval or just-in-time access outside business hours. | Security Operations Lead | 30 days | finding04_after_hours_logins.png | NIST CSF 2.0: DE.CM ¦ ISO/IEC 27001:2022: A.8.15, A.8.16 | Open
Rating scale
Risk score = Likelihood x Impact (each 1-5). Low: 1-4 ¦ Medium: 5-9 ¦ High: 10-16 ¦ Critical: 17-25.
Blue cells are inputs: change Likelihood or Impact and the score and rating update. Likelihood and impact values are my own judgment for this fictional case.
Framework mappings are suggested category-level references; verify against the current NIST CSF 2.0 and ISO/IEC 27001:2022 texts before presenting.

## Control Test
Control Test - MFA for All Active Accounts
Linked risk: R-03. Source: Splunk, index it_services_co.
Field | Detail
Control tested | All active employee accounts must use multi-factor authentication (MFA).
Test procedure | In Splunk, searched successful logins by active employees and grouped them by username and MFA status.
Splunk search | index=it_services_co employee_status=Active login_result=SUCCESS ¦ stats count by username, mfa_used
Population (active accounts) | 10
Accounts without MFA | 3
Failure rate | 30%
Accounts failing | rpatel (Admin), tnguyen (Developer), pjones (Analyst)
Result | Control FAILED
Finding | MFA is not consistently enforced. One failing account (rpatel) has admin privileges.
Risk rating | High
Recommended remediation | Require MFA enrollment for all accounts, starting with the admin account; add a policy that blocks password-only logins.
Evidence required | Enforcement policy screenshot; updated MFA enrollment report; retest results.
Evidence collected | finding05_mfa_control_test.png
Owner | Identity and Access Management (IAM) Lead
Due date | Admin account: 7 days; remaining accounts: 30 days
Status | Open
Retest search | index=it_services_co employee_status=Active login_result=SUCCESS mfa_used=No ¦ stats count by username
Retest pass criteria | Zero accounts returned. If any remain, the finding stays open.